## Agile_Project_Plan
Datenerfassung und -abstraktion von Industrieanlagen mittels OPC UA
	Projektname	Projektteam	Beginn	Ende
	Datenerfassung und -abstraktion von Industrieanlagen mittels OPC UA	Ondrej Hruby, Michael Mölle	13. Sep 19	03. Feb 20

	Arbeitsschritte	Beschreibung			Start	Ende	Dauer in Tagen	Status	Kommentare
	Meilenstein 1				13.9.19	25.10.19	42
	1	Dokumentation			13.9.19	2.3.20	171	In Arbeit
	2	Beschaffung von Software und Lizenzen			13.9.19	10.10.19	27	In Arbeit	War vorerst bis zum 30.09.2019 geplant. Bis heute (30.09.2019) weder Zugang zur Software vor Ort, noch Lizenz erhalten
	3	Konfiguration der virtuellen Maschine			23.9.19	3.10.19	10	In Arbeit
	4	Installation der Software „Visual Components 1.7.0“			10.10.19	11.10.19	1
	5	Installation der Software „UA Expert“ (virtuelle Maschine)			3.10.19	3.10.19	1
	6	Installation/ Konfiguration des Fließbandsensors			12.10.19	24.10.19	13
	Meilenstein 2				25.10.19	13.12.19	49
	1	Installation/ Konfiguration des OPC-UA-Server (C++)			14.10.19	25.10.19	11
	2	Installation/ Konfiguration des OPC-UA-Client			25.10.19	31.10.19	6
	3	Implementierung des OPC-UA-Clients in Visual Components			1.11.19	30.11.19	29
	4	Herstellen der Server-Client-Verbindung			1.12.19	13.12.19	12
	Meilenstein 3				13.12.19	21.2.20	70
	1	Konfiguration von node-red			13.12.19	2.1.20	20
	2	Erstellen eines node-red-Dashboards			3.1.20	16.1.20	13
	3	Datenauswertung			17.1.20	24.1.20	7
	4	Fertigstellung Dokumentation			27.1.19	21.2.20	19

## Agile_Project_Plan_-_BLANK
AGILE PROJECT PLAN TEMPLATE
	PROJECT NAME	PROJECT MANAGER	START DATE	END DATE		OVERALL PROGRESS		PROJECT DELIVERABLE
					SCOPE STATEMENT

AT RISK	TASK NAME	FEATURE TYPE	RESPONSIBLE	STORY POINTS	START	FINISH	DURATION (DAYS)	STATUS	COMMENTS
	Sprint 1
	Feature 1
	Feature 2
	Feature 3
	Sprint 2
	Feature 4
	Feature 5
	Feature 6
	Sprint 3
	Feature 7
	Feature 8
	Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.